## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

Throughout the 2015-2019 Consolidated plan years, the City of Columbus has worked to restructure the CDBG program to ensure that projects better align with identified community needs, and to ensure full compliance with CDBG regulations and Uniform Guidance. Over these years the City has taken a critical look at our own internal structure and the performance of our sub recipients. In addition, the city completed the 2020-2024 consolidated planning process. During that process citizens identified neighborhood infrastructure and reinvestment has a priority need.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assist low to moderate income owner-occupied homes | Affordable Housing |  | Homeowner Housing Added | Household Housing Unit | 85 | 8 | 9.41% |  |  |  |
| Assist low to moderate income owner-occupied homes | Affordable Housing |  | Homeowner Housing Rehabilitated | Household Housing Unit | 3525 | 12 | 0.34% | 700 | 112 | 16.00% |
| Assist low to moderate income owner-occupied homes | Affordable Housing |  | Direct Financial Assistance to Homebuyers | Households Assisted | 250 | 43 | 17.20% |  |  |  |
| Collaborate with CMHA on public housing activities | Public Housing |  | Other | Other | 0 | 0 |  | 1 | 0 | 0.00% |
| Decrease the incidence of STIs | Non-Homeless Special Needs Public Health |  | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 6500 | 0 | 0.00% | 1300 | 0 | 0.00% |
| Ensure equal access to housing | Affordable Housing Public Housing Fair Housing |  | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 250 | 0 | 0.00% | 1000 | 0 | 0.00% |
| Ensure safe and sanitary property conditions | Non-Housing Community Development |  | Homeowner Housing Rehabilitated | Household Housing Unit | 3500 | 0 | 0.00% |  |  |  |
| Ensure safe and sanitary property conditions | Non-Housing Community Development |  | Housing Code Enforcement/Foreclosed Property Care | Household Housing Unit | 16600 | 0 | 0.00% | 3320 | 0 | 0.00% |
| Foster business expansions in areas of need | Non-Housing Community Development |  | Facade treatment/business building rehabilitation | Business | 55 | 0 | 0.00% | 11 | 0 | 0.00% |
| Foster business expansions in areas of need | Non-Housing Community Development |  | Jobs created/retained | Jobs | 80 | 0 | 0.00% | 35 | 0 | 0.00% |
| Foster business expansions in areas of need | Non-Housing Community Development |  | Businesses assisted | Businesses Assisted | 75 | 173 | 230.67% | 185 | 173 | 93.51% |
| Foster development of skills for residents in need | Non-Housing Community Development |  | Other | Other | 0 | 0 |  |  |  |  |
| Housing for groups ineligible for public housing | Affordable Housing Non-Homeless Special Needs |  | Other | Other | 0 | 0 |  |  |  |  |
| Identify locations for economic reinvestment | Non-Housing Community Development |  | Businesses assisted | Businesses Assisted | 110 | 0 | 0.00% |  |  |  |
| Improve access to healthy food | Non-Housing Community Development |  | Other | Other | 0 | 0 |  |  |  |  |
| Improve pedestrian accessibility | Non-Housing Community Development |  | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 3785 |  | 0 | 3785 |  |
| Improve pedestrian accessibility | Non-Housing Community Development |  | Other | Other | 0 | 0 |  |  |  |  |
| Increase access to housing and emergency shelter | Affordable Housing Homeless |  | Overnight/Emergency Shelter/Transitional Housing Beds added | Beds | 22000 | 133722 | 607.83% | 4000 | 133722 | 3,343.05% |
| Increase access to housing and emergency shelter | Affordable Housing Homeless |  | Homelessness Prevention | Persons Assisted | 1000 | 0 | 0.00% | 2000 | 0 | 0.00% |
| Increase access to housing and emergency shelter | Affordable Housing Homeless |  | Other | Other | 10000 | 0 | 0.00% |  |  |  |
| Preserve and expand affordable housing | Affordable Housing |  | Rental units constructed | Household Housing Unit | 1260 | 127 | 10.08% | 140 | 127 | 90.71% |
| Preserve and expand affordable housing | Affordable Housing |  | Rental units rehabilitated | Household Housing Unit | 685 | 9 | 1.31% | 10 | 9 | 90.00% |
| Preserve and expand affordable housing | Affordable Housing |  | Homeowner Housing Added | Household Housing Unit | 85 | 43 | 50.59% | 12 | 8 | 66.67% |
| Preserve and expand affordable housing | Affordable Housing |  | Homeowner Housing Rehabilitated | Household Housing Unit | 0 | 0 |  | 3 | 0 | 0.00% |
| Preserve and expand affordable housing | Affordable Housing |  | Direct Financial Assistance to Homebuyers | Households Assisted | 0 | 43 |  | 60 | 43 | 71.67% |
| Preserve and expand affordable housing | Affordable Housing |  | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 0 | 43 |  | 175 | 70 | 40.00% |
| Program Management | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG: $3650514 / HOME: $511166 | Public service activities for Low/Moderate Income Housing Benefit | Households Assisted | 0 | 1614 |  | 375 | 103 | 27.47% |
| Program Management | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG: $3650514 / HOME: $511166 | Other | Other | 1 | 0 | 0.00% | 19 | 0 | 0.00% |
| Provide clean lots for redevelopment/green space | Non-Housing Community Development |  | Other | Other | 5 | 0 | 0.00% | 1 | 0 | 0.00% |
| Provide educational/recreational youth programs | Non-Housing Community Development |  | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 2500 | 0 | 0.00% |  |  |  |
| Provide educational/recreational youth programs | Non-Housing Community Development |  | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 18700 | 258 | 1.38% | 740 | 0 | 0.00% |
| Provide homebuyer education and assistance | Affordable Housing |  | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 250 | 1614 | 645.60% | 0 | 0 |  |
| Provide homebuyer education and assistance | Affordable Housing |  | Public service activities for Low/Moderate Income Housing Benefit | Households Assisted | 0 | 0 |  | 50 | 1614 | 3,228.00% |
| Provide housing access for persons with HIV/AIDS | Affordable Housing Non-Homeless Special Needs |  | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 495 | 0 | 0.00% | 99 | 0 | 0.00% |
| Provide housing access for persons with HIV/AIDS | Affordable Housing Non-Homeless Special Needs |  | Homelessness Prevention | Persons Assisted | 100 | 0 | 0.00% | 20 | 0 | 0.00% |
| Provide housing access for persons with HIV/AIDS | Affordable Housing Non-Homeless Special Needs |  | HIV/AIDS Housing Operations | Household Housing Unit | 595 | 0 | 0.00% | 20 | 0 | 0.00% |
| Provide housing assistance to elderly residents | Affordable Housing Non-Homeless Special Needs |  | Rental units constructed | Household Housing Unit | 200 | 0 | 0.00% |  |  |  |
| Provide housing assistance to elderly residents | Affordable Housing Non-Homeless Special Needs |  | Homeowner Housing Rehabilitated | Household Housing Unit | 1500 | 0 | 0.00% |  |  |  |
| Provide housing for special needs populations | Affordable Housing Non-Homeless Special Needs |  | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 0 |  | 1230 | 0 | 0.00% |
| Provide housing for special needs populations | Affordable Housing Non-Homeless Special Needs |  | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 1370 | 0 | 0.00% |  |  |  |
| Provide housing for special needs populations | Affordable Housing Non-Homeless Special Needs |  | Homelessness Prevention | Persons Assisted | 100 | 0 | 0.00% |  |  |  |
| Provide housing for special needs populations | Affordable Housing Non-Homeless Special Needs |  | Housing for Homeless added | Household Housing Unit | 200 | 0 | 0.00% |  |  |  |
| Reduce the infant mortality rate | Non-Homeless Special Needs Public Health |  | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 500 | 0 | 0.00% | 130 | 0 | 0.00% |
| Reduce the infant mortality rate | Non-Homeless Special Needs Public Health |  | Public service activities for Low/Moderate Income Housing Benefit | Households Assisted | 250 | 1614 | 645.60% |  |  |  |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

The result of the actions mentioned in the above section, the city completed a substantial amendment to the Consolidated Plan and spent a greater portion of it's CDBG resources on infrastructure such as road resurfacing, street lighting projects, and neighborhood facilities.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

For the 2019 CDBG Program, of the 1025 families assisted, about 61% of beneficiaries were Black or African American. According to the 2018 American Community Survey, the City of Columbus’ Black or African American population is a little less than 30% of all residents. The population of White residents who benefited from the program was approximately 35% of the 1025 families assisted. About 16% of CDBG program beneficiaries are Hispanic.

Approximately 83% of the families who benefited from the 2019 City of Columbus HOME Program were Black or African American. Almost 71% of families who benefited from the 2019 City of Columbus ESG Program were Black or African American.

For all of the City of Columbus HUD funded programs in 2019, only a handful of residents served identified as Native Hawaiian or Other Pacific Islander, American Indian or American Native or Asian. Approximately 2% of those served by the HUD programs in 2019 were Native Hawaiian or Other Pacific Islander, American Indian or American Native or Asian. According to the 2018 American Community Survey, the City of Columbus’ total population is about 6.5% Native Hawaiian or Other Pacific Islander, American Indian or American Native or Asian.

Please note that the HOPWA CAPER tracks program recipients slightly different from what is noted above. For additional information on the 2019 HOPWA outcomes, please see the HOPWA CAPER. Similar trends for the HOPWA outcomes when considering Race and Ethnicity were found when reporting. About 63% of the total served with the 2019 HOPWA program were Black or African American and about 37% of the total served with the 2019 HOPWA program were White.

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 18,949,987 | 12,485,344 |
| HOME | public - federal | 4,550,000 | 2,856,137 |
| HOPWA | public - federal | 2,323,706 | 1,151,449 |
| ESG | public - federal | 597,045 | 433,432 |

Table 3 - Resources Made Available

Narrative

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |

Table 4 – Identify the geographic distribution and location of investments

Narrative

The City did not identify any target area(s) for the 2019 HUD programs. Most of the programs are citywide initiative made available to all residents who qualify based on income and household size. One example of city-wide programing is the Fair Housing Program, made available to all residents in the City who feel they have been discriminated against during their pursuit for housing. Another example of citywide CDBG funded programing is the Neighborhood Liaisons activity. Each neighborhoods association and City Area Commission is assigned a Neighborhood Liaison.

The City of Columbus funded the Neighborhood Crisis Response Program with CDBG dollars which worked in the South Side neighborhoods, the Hilltop neighborhood, and the Linden neighborhoods. These neighborhoods are LMA, and were chosen for the programing due to an increase in violent crimes, gun violence, and sex trafficking in the neighborhoods.

Infrastructure investment and planning efforts were mostly concentrated in the Hilltop, south side and Linden communities as well during the 2019 CDBG program year. These are neighborhoods with communities which have experienced increases in a lack of private investment, number of failing schools and infant mortality rates.

The City’s HOME, ESG and HOPWA programs do not target geographic areas. Those programs are citywide.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

The city currently does not track leveraged funds.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | 69,285,436 |
| 2. Match contributed during current Federal fiscal year | 1,202,614 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | 70,488,050 |
| 4. Match liability for current Federal fiscal year | 318,676 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 70,169,375 |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |
| CHN Marsh Brook Place | 09/30/2019 | 343,604 | 0 | 0 | 0 | 0 | 0 | 1,202,614 |
| CHN Parsons Place | 09/30/2019 | 859,010 | 0 | 0 | 0 | 0 | 0 | 859,010 |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at begin-ning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |
| 0 | 449,926 | 0 | 325,000 | 449,926 |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Dollar Amount | 0 | 0 | 0 |
| Number | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 6,000 | 3,274 |
| Number of Non-Homeless households to be provided affordable housing units | 900 | 112 |
| Number of Special-Needs households to be provided affordable housing units | 100 | 54 |
| Total | 7,000 | 3,440 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 65 | 67 |
| Number of households supported through The Production of New Units | 268 | 135 |
| Number of households supported through Rehab of Existing Units | 925 | 121 |
| Number of households supported through Acquisition of Existing Units | 0 | 43 |
| Total | 1,258 | 366 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

During 2019, the Housing Division saw limited success toward its goals.  The number of CHDO units and Homeownership Development units were close to the goals established, as was the tenant based rental assistance program.  The number of completed rental units was due to slow flow of information from property owners as projects are completed.  Our Downpayment Assistance program continued to be a challenge with a hot homeownership market and sellers unwilling to wait the required period of time needed to process the applications.  While Home Repair needs continue to be a significant issue in the community, our subrecipient partners dealt with staff turnover that slowed their ability to address these needs.  The one goal we were thankful to not meet was the number of households needing optional relocation due to emergency vacate orders from Code Enforcement.

Discuss how these outcomes will impact future annual action plans.

These outcomes will not impact future annual action plans.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 199 | 1 |
| Low-income | 248 | 10 |
| Moderate-income | 240 | 7 |
| Total | 687 | 18 |

Table 13 – Number of Households Served

Narrative Information

The city has assisted more households than what is reported in this CAPER. However, the city was not able to track outcomes for all projects in time to complete this report, given the disruption due to COVID-19.

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

Each year, the City of Columbus investsgeneral fund dollars to the Maryhaven Collaborative Outreach Team (MCOT). MCOT uses a strategy to provide referrals to medical and behavioral healthcare and linkage to shelter and housing.

Addressing the emergency shelter and transitional housing needs of homeless persons

Please see the ESG CAPER and the COC rebuilding lives program for more information.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

As a member of the Columbus and Franklin County Continuum of Care (CoC, the city works with the (CoC) to create a path to housing from mental health facilities in partnership with the ADAMH Board of Franklin County. The city also invests in both Huckleberry House and OSU Star House who respectively serve runaway and homeless youth.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

Each year, the city commits general fund dollars to the Rebuilding lives Collaborative. More information on the funding for that program can be found on the ESG reports.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

The City of Columbus is actively engaged with the Columbus Metropolitan Housing Authority in the redevelopment of Poindexter Village which has received a Choice Neighborhoods grant.  Activities include the redevelopment of infrastructure, funding for new multifamily units, and homeownership opportunities adjacent to the development.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

The City of Columbus works with the Columbus Metropolitan Housing Authority to provide first time homebuyer assistance to homeownership voucher recipients.

Actions taken to provide assistance to troubled PHAs

CMHA is not a troubled PHA

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

During 2018, the City did a major re-write of tax abatement policies.  In areas that are market ready or ready for revitalization, developers must set aside 10% of the units to be occupied by and affordable to households at or below 80% AMI and 10% of the units to be occupied by and affordable to households at or below 100% AMI.  These requirements generally become effective in 2019.  In late 2019 the City, MORPC and the larger 7 county region began an affordable housing study to take a closer look at barriers to providing safe, affordable housing to all residents of Central Ohio. Multiple representatives from the City of Columbus including representatives from the Housing divison and the Grants Management team are participatig in this effort.

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

The city identified "affordable housing preservation and development" and "the provision of safe and sanitary housing" as priority needs. The City of Columbus has several programs in place that address these obstacles. Developers, using low-income housing tax credits, receive guidance, support and HOME funds to provide affordable rental housing.  These units serve very low income, low income and special needs populations in the community.

For those individuals most in need, the city provides programs for owner-occupied housing rehabilitation, emergency repair, and critical repairs for seniors living in their homes. By using federal funds and local bond dollars, the city funds vacancy prevention programs in the City. These programs provide the necessary assistance to allow homeowners to remain in a safe and sanitary home and prevent further vacant housing.

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

The city receives federal funds from HUD to conduct activities in compliance with the Office of Healthy Homes and Lead Hazard Control. In the City of Columbus, Lead Safe Columbus has the primary over-sight for the application of the Residential Lead Based Paint Hazard and Reduction Act of 1992. This policy applies to properties built before 1978 and in work areas where painted surfaces will be disturbed. Lead hazard control, lead education, outreach and research are the focus of the program. All city funded rehabilitation projects over $25,000 per unit must pass a lead assessment. The city recieved a 2019 Lead Harzards reduction grant to continue these efforts.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

The city continues to provide down payment assistance to low and moderate income first time homebuyers. In 2019, using a total of $250,460.88, 57 new homeowners received down payment assistance.  An additional $145,610.75 was provided to rehab 127 homes and $45,000 was spent to educate 1137 on homeowenrship.

Further, city programming through Rec and Parks is collaborative with Youth Family Services which offers a paid summer youth program. The Capital Kids program predominantly targets poverty-level families. This program assists families with homework help, behavior diagnosis and redirection, mentorship, drug and violence prevention strategies, food and meal resources for families such as job and housing opportuities and overall health and wellness. The School's Out program continues to serve poverty-level familiies by assisting with meals, trauma informed care, redirection, mentorship, physical fitness, and overall health and wellness.

In 20119, the City also completed a large scale restructuring of it's programming focused on small business development. The city is in the working stages of building new programming to related to this effort.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

The City of Columbus provides operating support to Community Housing Development Organizations (CHDOs), through the Community Development (CD) Collaborative of Greater Columbus, to encourage sustained capacity of local CHDOs. The CD Collaborative of Greater Columbus is a non-profit organization that pools resources to provide operating grants and technical assistance to build the capacity of community based non-profit housing developers. The CD Collaborative Board is comprised of various lending institutions including United Way of Central Ohio, The Columbus Foundation, and the City of Columbus and Franklin County. Staff for the Collaborative is provided through a contractual relationship with the Affordable Housing Trust for Columbus and Franklin County.

The Housing Division partners with local agencies and contractors to deliver services to the community in the areas of new rental housing, homeownership, owner-occupied housing rehabilitation, rental rehabilitation, construction of affordable homes and homebuyer education. In addition the city contracts with agencies that provide minor home repair services to the elderly and disabled as well as the Columbus Urban League to provide fair housing services to city residents.

Rec & Parks staff ensure that class sessions are instructed by a qualified instructor. Classes are advertised through social media and program guides are distributed throughout the city.

Grants Management spear headed efforts to increase the capacity of City staff involved with HUD funding throughout 2019. This included hosting training from The National Community Development Association, as well as creating a bimonthly working group to better track progress of CDBG funded programming. As part of the Consolidated Planning process, Grants Management Facilitated a SWOT analysis with 4 other city departments to identify weaknesses in the program as currently structured. Significant changes are in the works for the 2020-2024 Consolidated plan years to build the city's internal capacity.

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

The city is actively engaged with the Columbus Metropolitan Housing Authority in the redevelopment of Poindexter Village which has received a Choice Neighborhoods grant. Activities include the redevelopment of infrastructure, funding for new multifamily units and homeownership opportunities adjacent to the development. Local housing nonprofits have joined together to form the Columbus Housing Alliance. The Alliance is exploring new ways and new funding sources for affordable housing development.

Further, with regard to Rec & Parks partners with Nationwide Children's Hospital for behavioral health services to families and consultation for City staff for various programs. Additionally, the department attends community meetings to ensure information is shared with housing developments and surrounding communities, and partners with CColumbus Public Health to support the distribution of cribs, child immunizations, and adult healthy living programs.

o   We attend community meetings to ensure information is shared with housing developments and surrounding communities.

We also partner with Columbus Public Health to support distribution of cribs, child immunization and adult healthy living programs

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

The City of Columbus continued to work with housing providers to develop quality housing in all areas of the city. Funds were provided for administrative costs to the Columbus Urban League (CUL) to enable them to provide fair housing services to the residents of the city. These services include increasing the awareness of fair housing issues, fair housing barrier elimination, housing discrimination redress and implementation of the Fair Housing Action Plan. The CUL provides fair housing education and training, investigates all alleged housing discrimination complaints, coordinates and conducts housing discrimination testing sets and affirmative marketing monitoring visits on HOME and other projects, conducts homebuyer and homeownership education classes and advertising promotions/campaigns in order to reach protected groups.

Rec & Parks ensures all facilities are open to all. If a translator is required, one is provided. There is an equal opportunity to participate in classes, special events, and programs. All of the four School's Out sites, located on the southeast, west, near east, and north sides of Columbus, addressed issues of equal opportunity by continuing to spread services to multiple areas in need of affordable camps within the city. One of the Capital Kids sites is located within walking distance of a homeless shelter.  The program has provided resources and services for a few of these parents and children to help move them beyond homelessness.

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

As required by the HOME regulations, all HOME rental projects are monitored annually, based on the number of assisted units. There are mortgages and restrictive covenants filed on all homebuyer activities. Any change in title requires notification to the city.

Rec & Parks program director holds staff meetings with site directors and also makes several visits per month to the sites to assure compliance and build community relations.

For the HOPWA program, the Department of Health monitors each subrecipient at least once per year.

Grants Management staff monitor both city staff and subrecipients of all four programs based on an internal risk assement. In addition, Grants Management periodically reviews invoices and other expenditures to ensure compliance with Uniform Guidance and Grants Based accounting.

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

Each year a draft of the CAPER is posted on the Grants Management website for citizen review. In addition, the City takes out a legal ad in the Dispatch to ensure citizens are aware that the CAPER is out for public comment. This year we did not recieve any comments.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

The City of COlumbus has spent the last 4 program years revualuating the effectiveness and appropriateness of it's CDBG program. As such, the last four Action Plans have seen a lot of changes, with new programs added and long standing programs moved onto other funding sources. The City plans to continue these efforts to improve CDBG into 2020.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

No

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

## CR-50 - HOME 24 CFR 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in 24 CFR §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

On-site inspections were completed on affordable rental housing projects. Property management is responsible for non-emergency compliance to be completed within 30 days. For each non-compliance issue noted, all property owners corrected the items within the compliance deadline. A compliance file review revealed inclusion of undated documents and missing current tenant income calculation forms. Again, non-compliance issues were corrected within the compliance deadline.

Below is a list of properties inspected in 2019, listed by month.

January- Ottawa Senior

February- Briggsdale I & II, Southpoint, Laurel Green, Dogwood, Hilltop Senior I & II

â¿¿March- Hawthorne Village, Inglewood, CHN West, CHN Terrace, CHN Jefferson, CHN Far North

â¿¿April- Cityview, Fieldstone, Franklinton Senior, Columbus Elderly II, Trabue Crossing, Career Gateway, Weinland Park, Mariemont, Greater Linden

May- Fairview, Joyce Homes, Kingsford, CHN Holt Rd., CHN University District, CHN East, Milo Grogan, Elim Homes

June- Marsh Run, Pheasant Run, Waterford, North Hamilton Senior, Providence Glen

August- Scholar House, Hilltop Homes I & II, Monarch Green

September- Van Buren, Mapleside, Level Green, Victorian Heritage

October- Commons at Chantry, Chestnut Senior, Poindexter Senior, Poindexter II, The Whitney, Riverlodge II & III, HHNF,  Fairwood Commons, Stratford Senior, Columbus Elderly I, Parsons Senior, Hegemon Senior

November- Commons at Livingston I & II, Commons at Grant, Commons at Buckingham, Corban Commons, Homes on the Hill

â¿¿December- YMCA

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 24 CFR 91.520(e) and 24 CFR 92.351(a)

The goal of the City of Columbus, Department of Development, Housing Division has as a goal to affirmatively further fair housing.  This goal includes

- Not tolerating any housing discrimination in the city.

- Promoting fair housing choice for all persons.

- Providing opportunities for inclusive patterns of housing occupancy regardless of race, color, religion, sex, familial status, disability and national origin.

- Promoting housing that is structurally accessible to, and usable by, all persons, particularly those with disabilities.

- Fostering compliance with the nondiscrimination provisions of the Fair Housing Act.

These goals are implemented through the City’s HOME program as follows:

Rental Housing

Pre-Application

All pre-application submissions for support letters for LIHTC, Federal Home Loan Bank and other sources must have an affirmative fair housing marketing plan submitted as part of the pre-application.  The submission will be reviewed by staff for compliance and reasonableness.

Formal Application

The formal application submission will provide an affirmative fair housing marketing plan which will be reviewed by staff for compliance and reasonableness.

Project Completion

Post completion, at the first monitoring visit, the submission to OHFA of the affirmative fair housing marketing plan will be provided to the City monitoring staff for the file.  The plan will be reviewed by staff for compliance and reasonableness.

Ongoing Monitoring

As part of the ongoing monitoring of the rental project, the monitoring staff will request the affirmative fair marketing plan.

Complaints

Any fair housing complaints will be forwarded to the Columbus Urban League, the City’s Fair Housing contractor.

Homeownership Development and American Dream Downpayment Initiative

Homebuyer Application

Information on all HOME funded homebuyers are gathered on race, ethnicity, gender, household size and income.

Complaints

Any fair housing complaints will be forwarded to the Columbus Urban League, the City’s Fair Housing contractor.

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

HOME program income is added to the HOME entitlement grant to create a pool of available resources.

Describe other actions taken to foster and maintain affordable housing. 24 CFR 91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing). 24 CFR 91.320(j)

## CR-55 - HOPWA 91.520(e)

Identify the number of individuals assisted and the types of assistance provided

Table for report on the one-year goals for the number of households provided housing through the use of HOPWA activities for: short-term rent, mortgage, and utility assistance payments to prevent homelessness of the individual or family; tenant-based rental assistance; and units provided in housing facilities developed, leased, or operated with HOPWA funds.

| Number of Households Served Through: | One-year Goal | Actual |
| --- | --- | --- |
| Short-term rent, mortgage, and utility assistance to prevent homelessness of the individual or family | 20 | 32 |
| Tenant-based rental assistance | 99 | 97 |
| Units provided in permanent housing facilities developed, leased, or operated with HOPWA funds | 0 | 14 |
| Units provided in transitional short-term housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Total | 119 | 143 |

Table 14 – HOPWA Number of Households Served

Narrative

Please see the attached HOPWA CAPER for 2019 outcomes.

## CR-58 – Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |

Table 15 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |

Table 16 – Qualitative Efforts - Number of Activities by Program

Narrative

## CR-60 - ESG 91.520(g) (ESG Recipients only)

ESG Supplement to the CAPER in e-snaps

For Paperwork Reduction Act

1. Recipient Information—All Recipients Complete

Basic Grant Information

| Recipient Name | COLUMBUS |
| --- | --- |

| Organizational DUNS Number | 051369916 |
| --- | --- |

| UEI |  |
| --- | --- |

| EIN/TIN Number | 316400223 |
| --- | --- |

| Indentify the Field Office | COLUMBUS |
| --- | --- |

| Identify CoC(s) in which the recipient or subrecipient(s) will provide ESG assistance | Columbus/Franklin County CoC |
| --- | --- |

ESG Contact Name

| Prefix | Ms |
| --- | --- |

| First Name | Lucie |
| --- | --- |

| Middle Name |  |
| --- | --- |

| Last Name | McMahon |
| --- | --- |

| Suffix |  |
| --- | --- |

| Title | Grants Management Coordinator |
| --- | --- |

ESG Contact Address

| Street Address 1 | 90 W. Broad Street |
| --- | --- |

| Street Address 2 |  |
| --- | --- |

| City | Columbus |
| --- | --- |

| State | OH |
| --- | --- |

| ZIP Code | - |
| --- | --- |

| Phone Number | 6146457492 |
| --- | --- |

| Extension |  |
| --- | --- |

| Fax Number |  |
| --- | --- |

| Email Address | LMMcMahon@columbus.gov |
| --- | --- |

ESG Secondary Contact

| Prefix | Ms |
| --- | --- |

| First Name | Emerald |
| --- | --- |

| Last Name | HernÃ¡ndez-Parra |
| --- | --- |

| Suffix |  |
| --- | --- |

| Title | Assistant Director, Special Projects |
| --- | --- |

| Phone Number | 6146686459 |
| --- | --- |

| Extension |  |
| --- | --- |

| Email Address | ELHernandezParra@columbus.gov |
| --- | --- |

2. Reporting Period—All Recipients Complete

| Program Year Start Date | 01/01/2019 |
| --- | --- |

| Program Year End Date | 12/31/2019 |
| --- | --- |

3a. Subrecipient Form – Complete one form for each subrecipient

Subrecipient or Contractor Name: COMMUNITY SHELTER BOARD City: Columbus State: OH Zip Code: 43215, 5848 DUNS Number: 619605363 UEI: Is subrecipient a victim services provider: N Subrecipient Organization Type: Other Non-Profit Organization ESG Subgrant or Contract Award Amount: 597045

## CR-65 - Persons Assisted

4. Persons Served

4a. Complete for Homelessness Prevention Activities

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 0 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 0 |

Table 16 – Household Information for Homeless Prevention Activities

4b. Complete for Rapid Re-Housing Activities

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 0 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 0 |

Table 17 – Household Information for Rapid Re-Housing Activities

4c. Complete for Shelter

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 0 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 0 |

Table 18 – Shelter Information

4d. Street Outreach

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 0 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 0 |

Table 19 – Household Information for Street Outreach

4e. Totals for all Persons Served with ESG

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 3,364 |
| Children | 886 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 4,250 |

Table 20 – Household Information for Persons Served with ESG

5. Gender—Complete for All Activities

|  | Total |
| --- | --- |
| Male | 3,017 |
| Female | 1,233 |
| Transgender | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 4,250 |

Table 21 – Gender Information

6. Age—Complete for All Activities

|  | Total |
| --- | --- |
| Under 18 | 886 |
| 18-24 | 245 |
| 25 and over | 3,119 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 4,250 |

Table 22 – Age Information

7. Special Populations Served—Complete for All Activities

Number of Persons in Households

| Subpopulation | Total | Total Persons Served – Prevention | Total Persons Served – RRH | Total Persons Served in Emergency Shelters |
| --- | --- | --- | --- | --- |
| Veterans | 0 | 0 | 0 | 0 |
| Victims of Domestic Violence | 529 | 0 | 0 | 0 |
| Elderly | 0 | 0 | 0 | 0 |
| HIV/AIDS | 0 | 0 | 0 | 0 |
| Chronically Homeless | 0 | 0 | 0 | 0 |

| Persons with Disabilities: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Severely Mentally Ill | 1,198 | 0 | 0 | 0 |
| Chronic Substance Abuse | 0 | 0 | 0 | 0 |
| Other Disability | 0 | 0 | 0 | 0 |
| Total (Unduplicated if possible) | 0 | 0 | 0 | 0 |

Table 23 – Special Population Served

## CR-70 – ESG 91.520(g) - Assistance Provided and Outcomes

10.  Shelter Utilization

| Number of New Units - Rehabbed | 0 |
| --- | --- |
| Number of New Units - Conversion | 0 |
| Total Number of bed-nights available | 0 |
| Total Number of bed-nights provided | 0 |
| Capacity Utilization | 0.00% |

Table 24	 – Shelter Capacity

11.  Project Outcomes Data measured under the performance standards developed in consultation with the CoC(s)

Please see the SAGES attachement for more detail on ESG performance metrics.

## CR-75 – Expenditures

11. Expenditures

11a. ESG Expenditures for Homelessness Prevention

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 |
| Expenditures for Rental Assistance | 0 | 0 | 6,694 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 0 | 0 | 0 |
| Expenditures for Homeless Prevention under Emergency Shelter Grants Program | 0 | 0 | 0 |
| Subtotal Homelessness Prevention | 0 | 0 | 6,694 |

Table 25 – ESG Expenditures for Homelessness Prevention

11b. ESG Expenditures for Rapid Re-Housing

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 |
| Expenditures for Rental Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 0 | 0 | 0 |
| Expenditures for Homeless Assistance under Emergency Shelter Grants Program | 279,596 | 83,756 | 220,616 |
| Subtotal Rapid Re-Housing | 279,596 | 83,756 | 220,616 |

Table 26 – ESG Expenditures for Rapid Re-Housing

11c. ESG Expenditures for Emergency Shelter

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 |
| Essential Services | 0 | 0 | 0 |
| Operations | 283,037 | 29,695 | 179,935 |
| Renovation | 0 | 0 | 0 |
| Major Rehab | 0 | 0 | 0 |
| Conversion | 0 | 0 | 0 |
| Subtotal | 283,037 | 29,695 | 179,935 |

Table 27 – ESG Expenditures for Emergency Shelter

11d. Other Grant Expenditures

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2017 | 2018 | 2019 |
| Street Outreach | 0 | 0 | 0 |
| HMIS | 22,670 | 0 | 0 |
| Administration | 0 | 0 | 26,186 |

Table 28 - Other Grant Expenditures

11e. Total ESG Grant Funds

| Total ESG Funds Expended | 2017 | 2018 | 2019 |
| --- | --- | --- | --- |
| 1,132,185 | 585,303 | 113,451 | 433,431 |

Table 29 - Total ESG Funds Expended

11f. Match Source

|  | 2017 | 2018 | 2019 |
| --- | --- | --- | --- |
| Other Non-ESG HUD Funds | 0 | 0 | 0 |
| Other Federal Funds | 0 | 0 | 0 |
| State Government | 0 | 0 | 0 |
| Local Government | 2,872,304 | 2,847,258 | 0 |
| Private Funds | 0 | 0 | 0 |
| Other | 0 | 0 | 0 |
| Fees | 0 | 0 | 0 |
| Program Income | 0 | 0 | 0 |
| Total Match Amount | 2,872,304 | 2,847,258 | 0 |

Table 30 - Other Funds Expended on Eligible ESG Activities

11g. Total

| Total Amount of Funds Expended on ESG Activities | 2017 | 2018 | 2019 |
| --- | --- | --- | --- |
| 6,851,747 | 3,457,607 | 2,960,709 | 433,431 |

Table 31 - Total Amount of Funds Expended on ESG Activities

Attachment

Required Certification for Federal Awards

HOPWA PERFORMANCE