## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

This could be an overview that includes major initiatives and highlights that were proposed and executed throughout the program year.

As can be seen from the chart below, the State made significant progress in meeting its expected goals during this program year, including assisting 686 homeless households with ESG, HOME and HOPWA funds; creating or rehabilitating 52 units of affordable housing with HOME and CDBG funds; and creating or improving public facilities and infrastructure affecting 21,774 households.

Highlights of the program year include the State’s success in developing and implementing several rental assistance programs that addressed and minimized homelessness for the following populations: 1) individuals who have an opioid addiction; 2) permanently disabled individuals on SSI who have exhausted their Emergency Assistance; and 3) families involved with the child welfare system. These programs continue to enhance the State’s significant commitment to reducing and ending homelessness.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assist homeless households | Homeless | CDBG: $ / HOPWA: $ / HOME: $ / ESG: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 1225 | 1013 | 82.69% | 481 | 493 | 102.49% |
| Assist homeless households | Homeless | CDBG: $ / HOPWA: $ / HOME: $ / ESG: $ | Homelessness Prevention | Persons Assisted | 500 | 477 | 95.40% | 100 | 193 | 193.00% |
| Assist homeless households | Homeless | CDBG: $ / HOPWA: $ / HOME: $ / ESG: $ | Housing for People with HIV/AIDS added | Household Housing Unit | 10 | 2 | 20.00% |  |  |  |
| Assist homeless households | Homeless | CDBG: $ / HOPWA: $ / HOME: $ / ESG: $ | Other | Other | 125 | 112 | 89.60% |  |  |  |
| Expand homeownership opportunities for low and mod | Affordable Housing | CDBG: $ / HOPWA: $ / HOME: $ / ESG: $ / 100 Percent Financing: $ / 100% Financing: $10000000 | Direct Financial Assistance to Homebuyers | Households Assisted | 250 | 70 | 28.00% | 50 | 0 | 0.00% |
| Foster community economic development | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 50380 | 66101 | 131.20% | 21000 | 21774 | 103.69% |
| Foster community economic development | Non-Housing Community Development | CDBG: $ | Businesses assisted | Businesses Assisted | 10 | 4 | 40.00% |  |  |  |
| Foster community economic development | Non-Housing Community Development | CDBG: $ | Other | Other | 0 | 0 |  | 3 | 1 | 33.33% |
| Increase the supply of affordable housing | Affordable Housing Homeless | CDBG: $1200000 / HOME: $ / ESG: $ / Housing Trust Fund: $5599220 / HTF: $ | Rental units constructed | Household Housing Unit | 50 | 12 | 24.00% | 54 | 6 | 11.11% |
| Increase the supply of affordable housing | Affordable Housing Homeless | CDBG: $1200000 / HOME: $ / ESG: $ / Housing Trust Fund: $5599220 / HTF: $ | Rental units rehabilitated | Household Housing Unit | 0 | 0 |  |  |  |  |
| Increase the supply of affordable housing | Affordable Housing Homeless | CDBG: $1200000 / HOME: $ / ESG: $ / Housing Trust Fund: $5599220 / HTF: $ | Homeowner Housing Added | Household Housing Unit | 50 | 10 | 20.00% | 3 | 0 | 0.00% |
| Increase the supply of affordable housing | Affordable Housing Homeless | CDBG: $1200000 / HOME: $ / ESG: $ / Housing Trust Fund: $5599220 / HTF: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 0 | 0 |  | 60 | 46 | 76.67% |
| Increase the supply of affordable housing | Affordable Housing Homeless | CDBG: $1200000 / HOME: $ / ESG: $ / Housing Trust Fund: $5599220 / HTF: $ | Other | Other | 0 | 0 |  | 98 |  | % |
| Neighborhood rehabilitation | Affordable Housing | CDBG: $ / HOME: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 450 | 394 | 87.56% |  |  |  |
| Revitalize municipalities (small cities) | Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 50380 | 66101 | 131.20% | 21000 | 21774 | 103.69% |
| Revitalize municipalities (small cities) | Non-Housing Community Development | CDBG: $ | Other | Other | 0 | 0 |  | 3 | 1 | 33.33% |
| Sandy Revitalization | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG-DR: $41000000000 / CDBG-R: $ | Rental units constructed | Household Housing Unit | 4500 | 3758 | 83.51% | 579 | 579 | 100.00% |
| Sandy Revitalization | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG-DR: $41000000000 / CDBG-R: $ | Homeowner Housing Added | Household Housing Unit | 0 | 0 |  | 0 | 0 |  |
| Sandy Revitalization | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG-DR: $41000000000 / CDBG-R: $ | Homeowner Housing Rehabilitated | Household Housing Unit | 7600 | 5099 | 67.09% | 439 | 439 | 100.00% |
| Sandy Revitalization | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG-DR: $41000000000 / CDBG-R: $ | Direct Financial Assistance to Homebuyers | Households Assisted | 300 | 347 | 115.67% | 0 | 0 |  |
| Sandy Revitalization | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG-DR: $41000000000 / CDBG-R: $ | Tenant-based rental assistance / Rapid Rehousing | Households Assisted | 1100 | 1788 | 162.55% | 1100 | 1788 | 162.55% |
| Sandy Revitalization | Affordable Housing Homeless Non-Homeless Special Needs Non-Housing Community Development | CDBG-DR: $41000000000 / CDBG-R: $ | Businesses assisted | Businesses Assisted | 1200 | 1188 | 99.00% | 1200 | 1188 | 99.00% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

Assess how the jurisdiction’s use of funds, particularly CDBG, addresses the priorities and specific objectives identified in the plan, giving special attention to the highest priority activities identified.

As the chart above demonstrates, and consistent with the priorities and specific objectives outlined in the 2017 Annual Plan, the State allocated the majority of its HUD funds to address the need for affordable housing, to increase and preserve existing affordable housing, to address the needs of households who were homeless or had special needs, and to address infrastructure and public facility needs, as well as neighborhood rehabilitation. The largest share of CDBG funds was allocated to public facility, infrastructure and housing rehabilitation activities. ESG funds were allocated to address the need for emergency shelter, transitional housing and rapid re-housing for people who were homeless throughout the State. HOME and HOPWA funds were used to support rental assistance for people who were homeless or at risk of homelessness and those who had special needs. HOME funds were also used to create new affordable housing units.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

Table 2 – Table of assistance to racial and ethnic populations by source of funds

Narrative

The State of New Jersey identifies priority needs and offers services and programs to eligible households regardless of race or ethnicity. The above table reflects the demographic information provided by our program participants.

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 6,169,148 | 373,735 |
| HOME | public - federal | 3,539,857 | 1,696,420 |
| HOPWA | public - federal | 1,366,352 | 331,788 |
| ESG | public - federal | 3,223,041 | 331,788 |
| Housing Trust Fund | public - federal | 5,599,220 | 11 |
| LIHTC | public - state | 21,051,331 | 2,105,133 |
| Other | public - federal | 4,200,000,000 | 2,807,000,000 |
| Other | public - state | 4,200,000,000 | 2,807,000,000 |

Table 3 - Resources Made Available

Narrative

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| CDBG - Eligible Towns | 100 | 100 | Small Cities |
| Sandy Impacted Counties | 100 | 99 |  |
| State of New Jersey | 100 | 100 |  |

Table 4 – Identify the geographic distribution and location of investments

Narrative

CDBG: New Jersey’s Community Development Block Grant program makes annual awards to non-entitlement areas, also known as Small Cities.  The CDBG program prioritizes funding for activities that principally benefit low- and moderate-income persons; at least 70% of the funds are used for activities that benefit persons of low- and moderate-income households. CDBG funds were allocated through a competitive process to eligible jurisdictions.

ESG: Emergency Solutions Grant funds were allocated statewide through a competitive process. Priority assistance was given to projects that addressed life and safety issues in emergency shelters and transitional housing facilities.

HOME: HOME funds were distributed throughout the State.  Priority assistance was given to non-entitlement HOME communities that showed a demonstrated need for these funds.  DCA also prioritized projects that were ready to proceed.

HOPWA:  The formula HOPWA grant (HOP-1) was restricted to the following counties: Atlantic, Cape May, Cumberland, Mercer, Salem and Warren.  The HOPWA Post-Incarcerated Program (HOP-2 competitive grant) vouchers were utilized statewide.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

The State satisfied the required matching requirements in the following manner:

- The Community Development Block Grant Program (CDBG) requires that administration funds expended in excess of $100,000 must be matched on a one-to-one basis; the match for CDBG was the Affordable Housing Trust Fund.

- The Emergency Solutions Grant Program (ESG) requires a one to one match; the match for ESG was provided by the Affordable Housing Trust Fund and the Homelessness Prevention Program.

- The HOME Program requires a 25% match; the match for HOME was the State Rental Assistance Program.

| Fiscal Year Summary – HOME Match |  |
| --- | --- |
| 1. Excess match from prior Federal fiscal year | 78,966,641 |
| 2. Match contributed during current Federal fiscal year | 20,000,000 |
| 3. Total match available for current Federal fiscal year (Line 1 plus Line 2) | 98,966,641 |
| 4. Match liability for current Federal fiscal year | 1,044,440 |
| 5. Excess match carried over to next Federal fiscal year (Line 3 minus Line 4) | 97,922,201 |

Table 5 – Fiscal Year Summary - HOME Match Report

| Match Contribution for the Federal Fiscal Year |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project No. or Other ID | Date of Contribution | Cash (non-Federal sources) | Foregone Taxes, Fees, Charges | Appraised Land/Real Property | Required Infrastructure | Site Preparation, Construction Materials, Donated labor | Bond Financing | Total Match |
| State Rental Assistance Program | 07/01/2017 | 20,000,000 | 0 | 0 | 0 | 0 | 0 | 0 |

Table 6 – Match Contribution for the Federal Fiscal Year

HOME MBE/WBE report

| Program Income – Enter the program amounts for the reporting period |  |  |  |  |
| --- | --- | --- | --- | --- |
| Balance on hand at begin-ning of reporting period $ | Amount received during reporting period $ | Total amount expended during reporting period $ | Amount expended for TBRA $ | Balance on hand at end of reporting period $ |
| 0 | 795,065 | 181,158 | 0 | 613,907 |

Table 7 – Program Income

Minority Business Enterprises and Women Business Enterprises – Indicate the number and dollar value of contracts for HOME projects completed during the reporting period

|  | Total | Minority Business Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |

| Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

|  | Total | Women Business Enterprises | Male |
| --- | --- | --- | --- |

| Contracts |  |  |  |
| --- | --- | --- | --- |
| Dollar Amount | 0 | 0 | 0 |
| Number | 0 | 0 | 0 |

| Sub-Contracts |  |  |  |
| --- | --- | --- | --- |
| Number | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 |

Table 8 - Minority Business and Women Business Enterprises

Minority Owners of Rental Property – Indicate the number of HOME assisted rental property owners and the total amount of HOME funds in these rental properties assisted

|  | Total | Minority Property Owners |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Dollar Amount | 0 | 0 | 0 | 0 | 0 | 0 |

Table 9 – Minority Owners of Rental Property

Relocation and Real Property Acquisition – Indicate the number of persons displaced, the cost of relocation payments, the number of parcels acquired, and the cost of acquisition

|  | Number | Cost |
| --- | --- | --- |
| Parcels Acquired | 0 | 0 |
| Businesses Displaced | 0 | 0 |
| Nonprofit Organizations Displaced | 0 | 0 |
| Households Temporarily Relocated, not Displaced | 0 | 0 |

| Households Displaced | Total | Minority Property Enterprises |  |  |  | White Non-Hispanic |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Alaskan Native or American Indian | Asian or Pacific Islander | Black Non-Hispanic | Hispanic |  |
| Number | 0 | 0 | 0 | 0 | 0 | 0 |
| Cost | 0 | 0 | 0 | 0 | 0 | 0 |

Table 10 – Relocation and Real Property Acquisition

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of Homeless households to be provided affordable housing units | 456 | 493 |
| Number of Non-Homeless households to be provided affordable housing units | 0 | 0 |
| Number of Special-Needs households to be provided affordable housing units | 125 | 100 |
| Total | 581 | 593 |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through Rental Assistance | 181 | 193 |
| Number of households supported through The Production of New Units | 30 | 6 |
| Number of households supported through Rehab of Existing Units | 60 | 46 |
| Number of households supported through Acquisition of Existing Units | 0 | 0 |
| Total | 271 | 245 |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

The figures were less than projected for the following reasons:

- ·         Monthly housing assistance payments were higher than anticipated.

- ·         The number of HOME and CDBG units that were completed (received a Certificate of Occupancy) was less than anticipated.

- ·         Housing Trust Fund money has been committed to 20 rental units that will be completed in FY 19.

Discuss how these outcomes will impact future annual action plans.

The State will take into consideration higher housing assistance payments and unanticipated delays in completing construction and rehabilitation when projecting outcomes.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 1,599 | 193 |
| Low-income | 4,116 | 6 |
| Moderate-income | 2,780 | 0 |
| Total | 8,495 | 199 |

Table 13 – Number of Households Served

Narrative Information

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

The State ensured outreach to homeless people (especially the unsheltered) through its contracts with community-based provider agencies. Providers funded through the Shelter Support Program, the Homelessness Prevention and Rapid-Re-Housing Program and the Homelessness Prevention Program were required to perform outreach to those who were homeless or at risk of homelessness to make them aware of the resources available. They were required to perform an assessment of households served and make referrals to needed services.  

      

      The Department of Community Affairs also required community-based provider agencies participating in its permanent housing initiatives for homeless people to conduct outreach and assess individual needs. The permanent supportive housing initiatives in this program year included:

- Providing 100 Housing Choice Vouchers to young adults referred by the Department of Children and Families who are involved with the child welfare system and are homeless or at risk of homelessness.

- Allocating $1.2 million to the State Rental Assistance Program (SRAP), Housing First Opioid Initiative to provide security deposits and at least 120 vouchers to long-term homeless individuals who have an opioid addiction.  The purpose of this initiative is to help stabilize homeless opioid addicts by providing housing and case management. During this program year, 46 households were issued vouchers.

- Issuing 468 SRAP vouchers, through the statewide Housing First Initiative, to chronically homeless and homeless veterans.

Addressing the emergency shelter and transitional housing needs of homeless persons

The State used Emergency Solutions Grant (ESG) funds to address life and safety needs in emergency shelters and transitional housing facilities to allow grantees to purchase equipment and furnishings that provide direct benefit to shelter residents, and to create new emergency beds when needed.   DCA granted $3,081,312 to 27 provider agencies to support these needs.

Through its Homelessness Prevention and Rapid Re-housing program (HPRP), the State provided transitional rental assistance and support to homeless households. Supportive services offered included financial assistance, case management, housing search and placement, and financial literacy training. DCA granted $3,200,000 to 9 provider agencies to support these needs.

DCA and the State Parole Board also continued to partner on the Another Chance program, which provided transitional housing assistance (up to six months) to inmates released from designated Department of Corrections facilities without a stable living arrangement in the community. The program operates in Camden, Newark, New Brunswick and Trenton.

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

To ensure that individuals and families who were most at risk of becoming homeless were connected with all available resources, DCA collaborated with other State agencies, community-based providers, and local Continuums of Care (CoCs).

DCA continued to provide temporary financial assistance to low and moderate-income households in imminent risk of homelessness due to a rental eviction through the Homelessness Prevention Program (HPP).  The HPP provided assistance to over 500 households.

To foster better coordination and planning between these entities, DCA required its grantees in the Homelessness Prevention Program (HPP), Homelessness Prevention and Rapid Re-housing (HPRP) and the Shelter Support Program (SSP) to actively participate in their County CoCs, to utilize the Homeless Management Information System (HMIS), and to participate in the annual Point-in-Time Count. These programs assisted over 3,200 homeless households.

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

As can be seen by this report, in the past program year DCA has had great success in implementing programs that assist people who are homeless to obtain and sustain permanent supportive housing. These initiatives include the following:

- SRAP Housing First initiative provided permanent housing and supportive services to 468 chronically homeless or homeless veterans.

- SRAP Housing First Opioid Initiative provided assistance to 46 long-term homeless individuals who have an opioid dependence.

- Keeping Families Together provided rental assistance and supportive services to extremely vulnerable families who are homeless or live in unstable housing, and who are involved with the child welfare system. The program issued 123 project-based vouchers and 78 tenant-based vouchers to these households.

- The State received HUD Continuum of Care funding (CoC), which provided rental assistance to 245 homeless persons with disabilities. Funds for this program were granted in Atlantic, Burlington, Cape May, Essex, Gloucester, Middlesex, Morris, Passaic and Warren Counties.

- The Department of Community Affairs provided 100 Housing Choice Vouchers to young adults referred by the NJ Department of Children and Families who are involved with the child welfare system and are homeless or at risk of homelessness.

DCA also continued to provide rental assistance to people who are homeless and working towards self-sufficiency through the HOME Tenant-Based Rental Assistance, Housing Choice Voucher, State Rental Assistance and the Veterans Administration Supportive Housing programs.

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

DCA continued to administer the Housing Choice Voucher program statewide, supporting approximately 23,000 households in New Jersey. In addition, DCA operated the State Rental Assistance Program which provides state-funded rental assistance to more than 4,000 households.

DCA has also created Opportunity Knocks, a program designed to assist 100 current voucher holders to re-locate to areas of high opportunity, away from areas with concentrations of poverty. The program is currently operating in Camden and Mercer Counties.

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

DCA operated the following programs to assist Housing Choice Voucher Program participants in pursuing home ownership:

The Section 8 Homeownership Program allows families who are receiving Section 8 rental assistance to use that assistance to help pay the mortgage on a home they buy.

To qualify the family must:

- Be a first-time homebuyer

- Be employed full time for at least one year with a minimum earned income of $25,000 (except elderly and disabled people for whom the minimum income requirement is 12 times the monthly SSI/SSD amount)

- Have a credit score of at least 670, and successfully complete housing counseling and homebuyer education

The Family Self-Sufficiency Program (FSS) assists low-income tenants to build assets and increase their earnings so that they can better meet their families’ needs and become independent of welfare assistance. As part of the program, DCA establishes an interest-bearing FSS escrow account for each participating family. An escrow credit, based on increases in earned income of the family, is credited to this account during the five-year term of the FSS contract.

Actions taken to provide assistance to troubled PHAs

DCA continued to work in conjunction with the local HUD field office in addressing the needs of struggling public housing authorities throughout the state. The State has also taken over the administration of vouchers for several troubled PHAs in the past and provided tenant protection vouchers to troubled projects.

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

Although the ability of the State to eliminate, or even mitigate, some of these barriers is limited, DCA continued to do the following:

- Partner with HMFA to provide credit counseling to very low-income and low-income Section 8 households interested becoming homeowners. In addition, through its Homelessness Prevention and Rapid Re-Housing Program, DCA continued to provide credit counseling to eligible households (30% or less of AMI) receiving prevention and rapid re-housing assistance.

- Apply for additional competitive vouchers through the Family Unification Program and the Mainstream Program.

- Provide CDBG funds for infrastructure.

- Place a high priority on the long-term preservation of existing, viable affordable housing stock.

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

To address underserved needs, DCA continued its significant investments (as described above) in several initiatives designed to prevent and reduce homelessness and provide housing for people with special needs. In addition, DCA administered several McKinney rental assistance programs for local Continuums of Care (CoCs) that otherwise would not be able to continue providing these resources for homeless and formerly homeless people.

DCA continued to collaborate with HUD and various state departments and agencies such as the NJ Housing and Mortgage Finance Agency, the NJ Redevelopment Authority and the NJ Economic Development Authority to sponsor training and technical assistance for local officials to increase knowledge of and access to available state and federal programs and resources.

As previously noted, DCA continued to administer the Housing Choice Voucher and State Rental Assistance Programs to make housing affordable to low-income participants. Each of these programs contains a project-based voucher component to assist in the creation of new affordable housing.

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

DHCR is administering a $10 million Lead-Safe Home Remediation Pilot Program. This program provides lead-safe remediation and energy efficiency improvements in one- and two- family residential units built prior to 1978. The program provides an expected average direct remediation cost per unit of $12,000.  In eligible households where an elevated blood lead level has been identified in a child under the age of six or in a pregnant woman and the local health department requires full lead abatement activities, the grant recipient may provide lead abatement services of up to $20,000 per property. To date, the program has provided lead-safe remediation assistance and deemed lead-safe a total of 229 units.  DCA has received an additional allocation of $10 million for this program in the State fiscal year 2019.

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

To address the needs of poverty-level families, DCA has provided significant rental assistance and emergency assistance. In the past program year, DCA has provided the following resources:

- DCA’s Community Services Block Grant (CSBG) Program allocated funds to Community Action Agencies to provide shelter, food, clothing, health care and social services to nearly 400,000 families in crisis at or below 125% of the federal poverty guideline. These agencies not only provide emergency relief, they also provide supports that empower individuals and families to become permanently more self-sufficient through programs such as job training and placement, literacy programs, financial management skills, rapid rehousing and housing supports to prevent families from falling into homelessness, innovative transportation services through Lyft to enable clients to obtain and keep jobs, commercial driver training and substance abuse counselling and treatment.

- As described above, DCA’s ESG programs supported the operations of 27 transitional and shelter facilities.

- DCA’s Low Income Home Energy Assistance Program (LIHEAP) and Weatherization Programs provided energy services to 289,054 low-income households.

- As described above, DCA’s SRAP, HOME, HOPWA and HCV programs provide rental assistance to over 32,000 low-income households.

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

The State continued to work with nonprofit organizations, Continuums of Care, and other State departments to address housing needs.

- Provided technical assistance and funds to Community Housing Development Organizations (CHDOs) operating in low- and moderate-income neighborhoods to build affordable housing.

- Maintained an excellent working relationship with the local Continuum of Cares and various State departments, including the Department of Health, the Department of Children and Families, and the Department of Human Services, in order to implement a statewide homelessness strategy.

- SRAP Keeping Families Together provided project-based and tenant-based vouchers to extremely vulnerable families who are homeless or live in unstable housing, and who are involved with the child welfare system. The goal of the program is to ensure that children are not removed from their families, or that families can reunify, with stable housing and services designed to support their tenancy.

- SRAP DHS SSI program provided rental assistance to 150 households transitioning from DHS’ Division of Family Development (DFD) demonstration housing programs who have a permanent disability and receive SSI, and who would be at risk of homelessness without this subsidy. 

      

      DCA through its Moving On initiative issued over 300 State Rental Assistance Program (SRAP) tenant-based vouchers to eligible disabled households who were receiving rental assistance from a HUD Continuum of Care (CoCs) permanent supportive housing voucher program or were a recipient of another supportive housing voucher program and no longer required the level of supportive services associated with that program. This initiative enabled the CoCs and the Department of Health to refill their vacated vouchers with homeless individuals or families in need of supportive housing.

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

The State continued its efforts to enhance coordination between housing and social service agencies by hosting the following Continuum of Care meetings:

- On February 22, 2018, DCA in partnership with Monarch Housing Associates held a meeting to discuss resources available for homelessness prevention, emerging practices in evaluating program impact, and how prevention programs can be integrated with coordinated assessment.

- On March 23, 2018, DCA held a meeting for Continuum of Care leads and representatives from the local Offices of Emergency Management to discuss the Code Blue legislation and challenges and lessons learned from this past winter.

- On April 16, 2018, DCA in collaboration with the Corporation for Supportive Housing and the HUD Newark Office held a meeting on coordinating prevention and rapid rehousing.

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

See attachment

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

All CDBG, ESG and HOME project activities are monitored at least once during the course of the projects' scope of work. The monitoring includes a review of the grantee’s project file, the facility constructed or rehabilitated, an inspection of relevant items (for rental development and rehabilitation projects), and a review of the financial processes that the grantee uses.

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

Pursuant to 24 CFR Part 91, citizen participation requirements for States, the State provides adequate notice at the opening of the comment period. The Draft CAPER was posted on the Division of Housing and Community Resources Website (http://www.nj.gov/dca/divisions/dhcr/) for a minimum of 30 days.  No comments were received.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

New Jersey’s federal allocation was slightly less than the previous year's appropriation.  The FFY 2017/SFY 2018 appropriation was decreased by $58,148 from FFY 2016/SFY 2017.  The State's FFY 2017/SFY 2018 Plan had to budget more for public facilities to address the high demand to improve deteriorated infrastructure.  To account for this demand and the smaller allocation of funds the housing rehabilitation program was reduced slightly.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

No

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

## CR-50 - HOME 91.520(d)

Include the results of on-site inspections of affordable rental housing assisted under the program to determine compliance with housing codes and other applicable regulations

Please list those projects that should have been inspected on-site this program year based upon the schedule in §92.504(d). Indicate which of these were inspected and a summary of issues that were detected during the inspection. For those that were not inspected, please indicate the reason and how you will remedy the situation.

See attachments

Provide an assessment of the jurisdiction's affirmative marketing actions for HOME units. 92.351(b)

DCA required all HOME units to utilize affirmative marketing strategies to ensure that minority households have the opportunity to obtain decent, affordable housing. In addition, the State continued to utilize the nonprofit community and the DCA website to notify residents about affordable housing programs.  The state has found nonprofits to be a valuable resource in identifying those households least likely to apply for the State’s programs.  The State believes that its affirmative marketing strategy is working effectively.

Refer to IDIS reports to describe the amount and use of program income for projects, including the number of projects and owner and tenant characteristics

NA

Describe other actions taken to foster and maintain affordable housing.  91.220(k) (STATES ONLY: Including the coordination of LIHTC with the development of affordable housing).  91.320(j)

Each year, the State awards the full allocation of 9% credits to 12-15 projects, which will construct or rehabilitate approximately 1,000 units of affordable rental housing. 50% of the credits are awarded to non-age restricted (family) projects. At least 20% are awarded to age-restricted (senior) projects and at least 12.5% are awarded to supportive housing projects. 60% of the tax credits in these cycles are awarded to low poverty suburban municipalities. The 4% tax credits are non-competitive and are used for projects that finance at least 50% of construction costs with tax-exempt bonds.

## CR-55 - HOPWA 91.520(e)

Identify the number of individuals assisted and the types of assistance provided

Table for report on the one-year goals for the number of households provided housing through the use of HOPWA activities for: short-term rent, mortgage, and utility assistance payments to prevent homelessness of the individual or family; tenant-based rental assistance; and units provided in housing facilities developed, leased, or operated with HOPWA funds.

| Number of Households Served Through: | One-year Goal | Actual |
| --- | --- | --- |
| Short-term rent, mortgage, and utility assistance to prevent homelessness of the individual or family | 0 | 0 |
| Tenant-based rental assistance | 100 | 100 |
| Units provided in permanent housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Units provided in transitional short-term housing facilities developed, leased, or operated with HOPWA funds | 0 | 0 |
| Total | 100 | 100 |

Table 14 – HOPWA Number of Households Served

Narrative

The program met the goal.

## CR-60 - ESG 91.520(g) (ESG Recipients only)

ESG Supplement to the CAPER in e-snaps

For Paperwork Reduction Act

1. Recipient Information—All Recipients Complete

Basic Grant Information

| Recipient Name | NEW JERSEY |
| --- | --- |

| Organizational DUNS Number | 806418075 |
| --- | --- |

| EIN/TIN Number | 216000928 |
| --- | --- |

| Indentify the Field Office | NEWARK |
| --- | --- |

| Identify CoC(s) in which the recipient or subrecipient(s) will provide ESG assistance | Atlantic City & County CoC |
| --- | --- |

ESG Contact Name

| Prefix | Mrs |
| --- | --- |

| First Name | Sheri |
| --- | --- |

| Middle Name | 0 |
| --- | --- |

| Last Name | Malnak |
| --- | --- |

| Suffix | 0 |
| --- | --- |

| Title | Administrator |
| --- | --- |

ESG Contact Address

| Street Address 1 | 101 S.Broad Street |
| --- | --- |

| Street Address 2 | 0 |
| --- | --- |

| City | Trenton |
| --- | --- |

| State | NJ |
| --- | --- |

| ZIP Code | - |
| --- | --- |

| Phone Number | 6099848453 |
| --- | --- |

| Extension | 0 |
| --- | --- |

| Fax Number | 6092929653 |
| --- | --- |

| Email Address | sheri.malnak@dca.nj.gov |
| --- | --- |

ESG Secondary Contact

| Prefix |  |
| --- | --- |

| First Name |  |
| --- | --- |

| Last Name |  |
| --- | --- |

| Suffix |  |
| --- | --- |

| Title |  |
| --- | --- |

| Phone Number |  |
| --- | --- |

| Extension |  |
| --- | --- |

| Email Address |  |
| --- | --- |

2. Reporting Period—All Recipients Complete

| Program Year Start Date | 07/01/2017 |
| --- | --- |

| Program Year End Date | 06/30/2018 |
| --- | --- |

3a. Subrecipient Form – Complete one form for each subrecipient

Subrecipient or Contractor Name

City

State

Zip Code

DUNS Number

Is subrecipient a vistim services provider

Subrecipient Organization Type

ESG Subgrant or Contract Award Amount

## CR-65 - Persons Assisted

4. Persons Served

4a. Complete for Homelessness Prevention Activities

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 193 |
| Children | 197 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 390 |

Table 16 – Household Information for Homeless Prevention Activities

4b. Complete for Rapid Re-Housing Activities

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 334 |
| Children | 366 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 700 |

Table 17 – Household Information for Rapid Re-Housing Activities

4c. Complete for Shelter

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 3,148 |
| Children | 2,654 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 1 |
| Total | 5,803 |

Table 18 – Shelter Information

4d. Street Outreach

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 0 |
| Children | 0 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 0 |
| Total | 0 |

Table 19 – Household Information for Street Outreach

4e. Totals for all Persons Served with ESG

| Number of Persons in Households | Total |
| --- | --- |
| Adults | 4,342 |
| Children | 3,268 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 1 |
| Total | 7,611 |

Table 20 – Household Information for Persons Served with ESG

5. Gender—Complete for All Activities

|  | Total |
| --- | --- |
| Male | 3,299 |
| Female | 4,264 |
| Transgender | 32 |
| Don't Know/Refused/Other | 14 |
| Missing Information | 2 |
| Total | 7,611 |

Table 21 – Gender Information

6. Age—Complete for All Activities

|  | Total |
| --- | --- |
| Under 18 | 3,268 |
| 18-24 | 863 |
| 25 and over | 3,479 |
| Don't Know/Refused/Other | 0 |
| Missing Information | 1 |
| Total | 7,611 |

Table 22 – Age Information

7. Special Populations Served—Complete for All Activities

Number of Persons in Households

| Subpopulation | Total | Total Persons Served – Prevention | Total Persons Served – RRH | Total Persons Served in Emergency Shelters |
| --- | --- | --- | --- | --- |
| Veterans | 0 | 3 | 2 | 116 |
| Victims of Domestic Violence | 0 | 11 | 30 | 491 |
| Elderly | 0 | 7 | 10 | 147 |
| HIV/AIDS | 0 | 0 | 0 | 24 |
| Chronically Homeless | 0 | 0 | 4 | 273 |

| Persons with Disabilities: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Severely Mentally Ill | 0 | 12 | 26 | 688 |
| Chronic Substance Abuse | 0 | 0 | 1 | 389 |
| Other Disability | 0 | 12 | 38 | 155 |
| Total (Unduplicated if possible) | 0 | 0 | 0 | 0 |

Table 23 – Special Population Served

## CR-70 – ESG 91.520(g) - Assistance Provided and Outcomes

10.  Shelter Utilization

| Number of New Units - Rehabbed | 0 |
| --- | --- |
| Number of New Units - Conversion | 0 |
| Total Number of bed-nights available | 365 |
| Total Number of bed-nights provided | 365 |
| Capacity Utilization | 100.00% |

Table 24	 – Shelter Capacity

11.  Project Outcomes Data measured under the performance standards developed in consultation with the CoC(s)

Performance outcomes:*

- At least 25 persons will receive emergency housing during the grant

- At least 75% of the beds in the shelter or transitional housing facility will be utilized per month

- A van purchased with program funds will be utilized at least 3 times per week for activities such as transporting clients to medical appointments, employment opportunities, laundromat, etc.

- The average length of stay in an emergency shelter will be no more than six months

- The average length of stay in a transitional housing facility will be not less than 6 months or more than 24 months

* Performance outcomes specific to the approved grant activities will be negotiated prior to the contract’s execution.

## CR-75 – Expenditures

11. Expenditures

11a. ESG Expenditures for Homelessness Prevention

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2015 | 2016 | 2017 |
| Expenditures for Rental Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 146,597 | 104,057 | 162,121 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 44,217 | 16,543 | 94,949 |
| Expenditures for Homeless Prevention under Emergency Shelter Grants Program | 0 | 0 | 0 |
| Subtotal Homelessness Prevention | 190,814 | 120,600 | 257,070 |

Table 25 – ESG Expenditures for Homelessness Prevention

11b. ESG Expenditures for Rapid Re-Housing

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2015 | 2016 | 2017 |
| Expenditures for Rental Assistance | 0 | 0 | 0 |
| Expenditures for Housing Relocation and Stabilization Services - Financial Assistance | 662,970 | 35,912 | 556,873 |
| Expenditures for Housing Relocation & Stabilization Services - Services | 284,130 | 113,846 | 241,845 |
| Expenditures for Homeless Assistance under Emergency Shelter Grants Program | 0 | 0 | 0 |
| Subtotal Rapid Re-Housing | 947,100 | 149,758 | 798,718 |

Table 26 – ESG Expenditures for Rapid Re-Housing

11c. ESG Expenditures for Emergency Shelter

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2015 | 2016 | 2017 |
| Essential Services | 0 | 0 | 175,286 |
| Operations | 84,026 | 102,536 | 340,014 |
| Renovation | 1,167,081 | 198,550 | 597,073 |
| Major Rehab | 0 | 0 | 252,147 |
| Conversion | 0 | 0 | 0 |
| Subtotal | 1,251,107 | 301,086 | 1,364,520 |

Table 27 – ESG Expenditures for Emergency Shelter

11d. Other Grant Expenditures

|  | Dollar Amount of Expenditures in Program Year |  |  |
| --- | --- | --- | --- |
|  | 2015 | 2016 | 2017 |
| Street Outreach | 0 | 0 | 0 |
| HMIS | 62,315 | 15,052 | 50,800 |
| Administration | 201,169 | 162,219 | 75,000 |

Table 28 - Other Grant Expenditures

11e. Total ESG Grant Funds

| Total ESG Funds Expended | 2015 | 2016 | 2017 |
| --- | --- | --- | --- |
| 5,947,328 | 2,652,505 | 748,715 | 2,546,108 |

Table 29 - Total ESG Funds Expended

11f. Match Source

|  | 2015 | 2016 | 2017 |
| --- | --- | --- | --- |
| Other Non-ESG HUD Funds | 0 | 0 | 0 |
| Other Federal Funds | 0 | 0 | 0 |
| State Government | 3,300,000 | 3,300,000 | 3,300,000 |
| Local Government | 0 | 0 | 0 |
| Private Funds | 0 | 0 | 0 |
| Other | 0 | 0 | 0 |
| Fees | 0 | 0 | 0 |
| Program Income | 0 | 0 | 0 |
| Total Match Amount | 3,300,000 | 3,300,000 | 3,300,000 |

Table 30 - Other Funds Expended on Eligible ESG Activities

11g. Total

| Total Amount of Funds Expended on ESG Activities | 2015 | 2016 | 2017 |
| --- | --- | --- | --- |
| 15,847,328 | 5,952,505 | 4,048,715 | 5,846,108 |

Table 31 - Total Amount of Funds Expended on ESG Activities

Attachment

Analysis of Impediments Update